**LOGFRAME TEMPLATE**

**Instructions:**

1. Define your project’s impact. Remember, your organization may already have an impact that they would like you to use.
2. Define your project’s inputs and outputs.
3. Define your project’s outcomes. Check to make sure that there is a strong logical flow between each level!
4. Find at least one risk or assumption for each level of your log frame.

**Project Title:** ZRCS-MNCH -SMAGs Project

**Date:10th October 2020 to 10th October 2023**

|  |  |  |
| --- | --- | --- |
| Planning for Monitoring and Evaluation |  | 1 |



|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **Project**  **Summary** | **Indicators** | **Means of Verifications** | **Risks and Assumptions** |
| **Impact** | To strengthen community participation in safe motherhood support services by 2023, through the establishment of SMAGs and participation in MDRs committees within the communities of Limulunga district. |  |  | The communities might not participate fully due to some customs and norms of the communities |
| **Outcomes** | The volunteers will have knowledge and skills in conducting community- based safe motherhood and child health services/community engagement and mobilization |  |  | * Not all volunteers would be active * The community might not accept the strategy * Few volunteers would prefer to work on voluntary basis |
| **Outputs** | Training of Red Cross volunteers/SMAGs in the SMAGs strategy, community-based safe motherhood and child health services. |  |  | * Not all volunteers would turn up for training as per target * Wrong people might be trained * Few volunteers would understand the strategy |
| **Inputs** | Recruitment of Red Cross community volunteers and establishment of SMAGs within the communities of Limulunga district. |  |  | * Few community members volunteer due to education levels * No funds to recruit volunteers |